## Hoja1
Tasks | Category | Status | Complete % | Estimated Date
Closer's OEs Report | Team Performance | Under Review | 85
Notes | 07/02/2018: Wasn’t able to test query as SP. Error: Msg 229, Level 14, State 5, Procedure get_closer_oes_report, Line 51 The EXECUTE permission was denied on the object 'get_closer_oes_report', database 'VIDA', schema 'dbo'.
Profile Writing Report | Team Performance | Not Started | 5
Notes
Average Spend and Margins by Package Level | Margins | On Hold | 50

## Hoja2
| Tasks | Status | % Complete | Comment
| Closer's OEs Report | Waiting feedback | 90 | Waiting on some fields and needed changes
| Profile Writing Report | Working | 90 | Working on requested changes from last 22/07 meeting with Ben
| Average Spend and Margins by Package Level | On Hold | 70 | Waiting to review with someone on the Business side
| R-PredictiveMessaging | On Hold |  | Available to run scripts on schedule days Automation pending
Meeting with Cat
1 | Reports clean up
| Writer reports | eliminate seconds

## 09-11-2018
Priority | Item # | Tasks | Request By | Status | % Complete | Comment | Meeting with Cat notes:
6 | 1 | Closer's OEs Report | Ben | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
1 | 2 | Profile Writing Report | Ben | done | 90 | Working on requested changes from last 22/07 meeting with Ben 09/10: Ben and Preeti requested to consider using #clients instead of units | Change to profile #
| 3 | Average Spend and Margins by Package Level | Scott | On Hold | 70 | Waiting to review with someone on the Business side
3 | 4 | R-PredictiveMessaging scripts |  | Working | 70 | 09/08: Available to run scripts on schedule days but with problems Automation pending | Meet with Guille and Derrick to discuss automation
5 | 5 | PM Effectiveness Report | Cat | Not started | 0 | Cat and I were chatting about a possible report to regularly see the impact of predictive messaging - do you think this is something you could help create? Most of the data we need is in Guille's extract, however, we would also need the field 'Predictive Messaging Template Used' - is it possible to pull this from the back end of Zoho? If we can do that, the rest of the report would be in summarizing the data.
2 | 6 | Add Client Status in 1. Client Progress Report | Meagan | done (Guille) | 0 | Field from Vida.accounts table
4 | 7 | CRM restore ETL | Guille | Not started | 0
7 | 8 | Cleaning/Maintain reports | Cat | Not started | 0 | Statistics on the use. Who is using it?
Cat schedule:
Monday 10:00 Tuesday 10:30 - 2:30pm Arg Thursday 10:30 (next Week) Wednesday 9:30, 10

## 09-20-2018
Priority | Item # | Tasks | Request By | Status | % Complete | Comment | Meeting with Cat notes:
6 | 1 | Closer's OEs Report | Ben | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
1 | 2 | Profile Writing Report | Ben | done | 90 | Working on requested changes from last 22/07 meeting with Ben 09/10: Ben and Preeti requested to consider using #clients instead of units | Change to profile #
| 3 | Average Spend and Margins by Package Level | Scott | On Hold | 70 | Waiting to review with someone on the Business side
3 | 4 | R-PredictiveMessaging scripts |  | Working | 70 | 09/08: Available to run scripts on schedule days but with problems Automation pending | Meet with Guille and Derrick to discuss automation
5 | 5 | PM Effectiveness Report | Cat | Not started | 0 | Cat and I were chatting about a possible report to regularly see the impact of predictive messaging - do you think this is something you could help create? Most of the data we need is in Guille's extract, however, we would also need the field 'Predictive Messaging Template Used' - is it possible to pull this from the back end of Zoho? If we can do that, the rest of the report would be in summarizing the data.
2 | 6 | Add Client Status in 1. Client Progress Report | Meagan | done (Guille) | 0 | Field from Vida.accounts table
4 | 7 | CRM restore ETL | Guille | Not started | 0
7 | 8 | Cleaning/Maintain reports | Cat | Not started | 0 | Statistics on the use. Who is using it?
| 9 | Margins by Client – failing | Scott | Not started |  | I was able to duplicate failure. Need to review and talk about changes on this report with Guille on next Sat meeting
| 10 | Gross Revenue per Customer | Scott | Not started |  | Seem to be a permission on datasource issue.
Cat schedule:
Monday 10:00 Tuesday 10:30 - 2:30pm Arg Thursday 10:30 (next Week) Wednesday 9:30, 10

## 10-02-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | done | 100 | Need to move this one to production svn | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Working | 70 | 10/01: Build up questions for Derrick. Waiting on him
2 |  | PM Effectiveness Report | Cat |  | Not started | 0 | Cat and I were chatting about a possible report to regularly see the impact of predictive messaging - do you think this is something you could help create? Most of the data we need is in Guille's extract, however, we would also need the field 'Predictive Messaging Template Used' - is it possible to pull this from the back end of Zoho? If we can do that, the rest of the report would be in summarizing the data.
3 |  | CRM restore ETL | Guille |  | Not started | 0
4 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
5 | 3 | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Working | 0
7 | 4 | Customer LTV | Scott | Add actual margins | Not started

## 10-09-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | done | 100 | Need to move this one to production svn | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Working | 70 | 10/01: Build up questions for Derrick. Waiting on him
2 |  | PM Effectiveness Report | Cat |  | Not started | 0 | Cat and I were chatting about a possible report to regularly see the impact of predictive messaging - do you think this is something you could help create? Most of the data we need is in Guille's extract, however, we would also need the field 'Predictive Messaging Template Used' - is it possible to pull this from the back end of Zoho? If we can do that, the rest of the report would be in summarizing the data.
3 |  | CRM restore ETL | Guille |  | Not started | 0
4 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
5 | 5 | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Working | 0
7 | 4 | Customer LTV | Scott | Add actual margins | Not started
8 | 3 | Report on Deposits |  | NEW | Not started |  | 1. we can have a client how has been with us and the pay for a new deposit – disregard 2. data from August 2018

## 10-23-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | done | 100 | Need to move this one to production svn | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Working | 70 | 10/01: Build up questions for Derrick. Waiting on him
2 |  | PM Effectiveness Report | Cat |  | Not started | 0 | Cat and I were chatting about a possible report to regularly see the impact of predictive messaging - do you think this is something you could help create? Most of the data we need is in Guille's extract, however, we would also need the field 'Predictive Messaging Template Used' - is it possible to pull this from the back end of Zoho? If we can do that, the rest of the report would be in summarizing the data.
3 |  | CRM restore ETL | Guille |  | Not started | 0
4 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
5 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
7 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
send email to Ben, Preeti about Writing performance report
Profile Writing Report: Create new task type or take first creation/edition task

## 11-06-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | Working | 100 | 11/05 Working on requested change Need to move this one to production svn | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Working | 20
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20

## 11-13-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | On hold | 100 | 11/05 Working on requested change 11/09 Waiting on Ben and Guille definition on this. | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Working | 20
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
9 |  | Time Log vs. Report Server Discrepancy | Kim |  | On Hold |  | Reviewed and got a solution 11/09 – set up on hold until Guille and users decide how to proceed

## 11-20-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | Working | 100 | 11/20: Had a meeting today with Preeti and we consolidate positions on the logic. I will upload the final test version tomorrow. | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Waiting on feedback | 20 | Sent some initial information on this report and waiting on some other question responses.
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
9 |  | Time Log vs. Report Server Discrepancy | Kim |  | On Hold |  | Reviewed and got a solution 11/09 – set up on hold until Guille and users decide how to proceed

## 11-27-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | Working | 100 | 11/27: Final reviews | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Working | 40 | Received Cat feedback. Reviewing data in order to build report. Will send new data for review tomorrow 11/28
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
9 |  | Time Log vs. Report Server Discrepancy | Kim |  | On Hold |  | Reviewed and got a solution 11/09 – set up on hold until Guille and users decide how to proceed

## 12-06-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | Working | 100 | 11/27: Final reviews | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Working | 40 | 12/06: Changed to Client Performance folder. Waiting for Guille’s feedback
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
9 |  | Time Log vs. Report Server Discrepancy | Kim |  | On Hold |  | Reviewed and got a solution 11/09 – set up on hold until Guille and users decide how to proceed

## 12-11-2018
# | Priority | Tasks Name | Request By | Description | Status | % Complete | Comment | Meeting with Cat notes:
1 |  | Closer's OEs Report | Ben |  | On hold | 90 | Waiting on some fields and needed changes 09/10: Meagan added client challenge level that needs to be considered on this report
2 | 1 | Profile Writing Report | Ben |  | Working | 100 | 11/27: Final reviews | Change to profile #
3 |  | Average Spend and Margins by Package Level | Scott |  | On Hold | 70 | Waiting to review with someone on the Business side
1 | 1 | R-PredictiveMessaging scripts |  |  | Done | 70 | 10/01: Build up questions for Derrick. Waiting on him
4 | 2 | PM Effectiveness Report | Cat |  | Working | 40 | 12/06: Changed to Client Performance folder. Waiting for Guille’s feedback
5 |  | CRM restore ETL | Guille |  | Not started | 0
6 |  | Cleaning/Maintain reports | Cat |  | Not started | 0 | Statistics on the use. Who is using it?
7 |  | Margins by Client | Scott | Add client active filter | Not started
6 | 2 | Time App Report Request | Meagan |  | Waiting on feedback | 0
8 |  | Customer LTV | Scott | Add actual margins | Not started
8 |  | Report on Deposits |  | NEW | Done |  | Completed as of 10/20
9 |  | Time Log vs. Report Server Discrepancy | Kim |  | On Hold |  | Reviewed and got a solution 11/09 – set up on hold until Guille and users decide how to proceed
New project – apply filter to every report Women and Man
Margins folder reports